## Risk Register
Risk_ID | Risk_Title | Risk_Category | Business_Unit | Risk_Owner | Likelihood | Impact | Risk_Score | Inherent_Risk | Control_Effectiveness | Residual_Risk | Mitigation_Status | Target_Date | Date_Identified | Last_Review_Date | Status
R001 | Unauthorized data access | IT Risk | Operations | Head of IT | 4 | 5 | 20 | High | Moderate | High | In Progress | 2025-12-01 | 2026-01-10 | 2026-03-01 | Open
R002 | Regulatory non-compliance | Compliance | Finance | Compliance Manager | 3 | 5 | 15 | High | Strong | Medium | In Progress | 2025-12-01 | 2026-01-15 | 2026-03-05 | Open
R003 | Vendor system outage | Third-Party Risk | Technology | Vendor Manager | 4 | 4 | 16 | High | Moderate | Medium | Not Started | 2025-12-01 | 2026-02-01 | 2026-03-10 | Open
R004 | Fraudulent transactions | Operational Risk | Retail Banking | Risk Officer | 3 | 5 | 15 | High | Moderate | Medium | In Progress | 2025-12-01 | 2026-01-05 | 2026-03-08 | Open
R005 | Data loss due to backup failure | IT Risk | Infrastructure | IT Lead | 2 | 5 | 10 | Medium | Weak | Medium | Not Started | 2025-12-01 | 2026-02-10 | 2026-03-12 | Open
R006 | Cybersecurity breach | Cyber Risk | Technology | Security Lead | 5 | 5 | 25 | High | Moderate | High | In Progress | 2026-09-01 | 2026-01-12 | 2026-03-03 | Open
R007 | Loan default increase | Financial Risk | Credit | Credit Manager | 4 | 4 | 16 | High | Moderate | Medium | In Progress | 2026-09-01 | 2026-01-20 | 2026-03-07 | Open
R008 | System downtime | IT Risk | Operations | IT Manager | 3 | 4 | 12 | Medium | Strong | Low | Completed | 2026-09-01 | 2026-01-18 | 2026-03-09 | Open
R009 | Customer churn | Strategic Risk | Marketing | Marketing Lead | 3 | 4 | 12 | Medium | Moderate | Medium | In Progress | 2026-09-01 | 2026-01-25 | 2026-03-11 | Open
R010 | Incorrect financial reporting | Compliance | Finance | Finance Manager | 2 | 5 | 10 | Medium | Strong | Low | Completed | 2026-09-01 | 2026-01-14 | 2026-03-02 | Open
R011 | Cloud service outage | IT Risk | Technology | Cloud Engineer | 4 | 4 | 16 | High | Moderate | Medium | In Progress | 2026-05-01 | 2026-02-05 | 2026-03-12 | Closed
R012 | Data governance failure | Data Risk | Operations | Data Manager | 3 | 4 | 12 | Medium | Weak | Medium | Not Started | 2026-05-01 | 2026-02-15 | 2026-03-14 | Closed
R013 | Insider fraud | Operational Risk | Finance | Internal Auditor | 3 | 5 | 15 | High | Moderate | Medium | In Progress | 2026-05-01 | 2026-01-22 | 2026-03-10 | Closed
R014 | API integration failure | Technology Risk | IT Systems | IT Architect | 2 | 4 | 8 | Medium | Strong | Low | Completed | 2026-05-01 | 2026-02-01 | 2026-03-09 | Closed
R015 | Third-party data breach | Third-Party Risk | Security | Vendor Risk Manager | 4 | 5 | 20 | High | Moderate | High | Not Started | 2026-05-01 | 2026-02-18 | 2026-03-15 | Closed
R016 | Phishing attack on employees | Cyber Risk | Security | Security Analyst | 4 | 4 | 16 | High | Moderate | Medium | In Progress | 2026-06-20 | 2026-02-20 | 2026-03-15 | Open
R017 | System upgrade failure | IT Risk | Technology | IT Manager | 3 | 4 | 12 | Medium | Moderate | Medium | Not Started | 2026-08-05 | 2026-02-22 | 2026-03-16 | Open
R018 | Incorrect data migration | Data Risk | IT Systems | Data Engineer | 3 | 5 | 15 | High | Weak | High | In Progress | 2026-06-30 | 2026-02-18 | 2026-03-12 | Open
R019 | Loss of key personnel | Operational Risk | HR | HR Manager | 3 | 4 | 12 | Medium | Moderate | Medium | Not Started | 2026-09-01 | 2026-02-25 | 2026-03-18 | Open
R020 | Customer data privacy violation | Compliance | Legal | Compliance Officer | 4 | 5 | 20 | High | Moderate | High | In Progress | 2026-06-10 | 2026-01-30 | 2026-03-14 | Open
R021 | Market volatility impact | Financial Risk | Finance | Finance Director | 4 | 4 | 16 | High | Moderate | Medium | Monitoring | 2026-07-25 | 2026-02-05 | 2026-03-10 | Monitoring
R022 | Delayed project delivery | Operational Risk | Projects | Project Manager | 3 | 3 | 9 | Medium | Strong | Low | Completed | 2026-05-30 | 2026-02-01 | 2026-03-08 | Closed
R023 | Weak access control | IT Security | Infrastructure | Security Lead | 4 | 5 | 20 | High | Weak | High | In Progress | 2026-06-15 | 2026-01-28 | 2026-03-13 | Open
R024 | Third-party contract failure | Third-Party Risk | Procurement | Procurement Manager | 3 | 4 | 12 | Medium | Moderate | Medium | Not Started | 2026-08-15 | 2026-02-12 | 2026-03-17 | Open
R025 | Regulatory policy change | Compliance | Legal | Compliance Manager | 3 | 4 | 12 | Medium | Moderate | Medium | Monitoring | 2026-07-10 | 2026-02-08 | 2026-03-11 | Monitoring